## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
2201-swen-261-05-a | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | PASS JT, 9-29-2020 | Pass | PASS JT, 10-20-2020
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | PASS JT, 9-29-2020 | Pass | PASS JT, 10-20-2020
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | PASS JT, 9-29-2020 | Pass | PASS JT, 10-20-2020
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | PASS JT, 9-29-2020 | Pass | PASS JT, 10-20-2020
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | PASS PO, 9-29-2020 | Pass | PASS PO, 10-20-2020
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | PASS PO, 9-29-2020 | Pass | PASS PO, 10-20-2020
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | PASS PO, 9-29-2020 | Pass | PASS PO, 10-20-2020
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | PASS AC, 9-30-2020 | Pass | PASS AC, 10-20-2020
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | PASS AC, 9-30-2020 | Pass | PASS AC, 10-20-2020
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | PASS AC, 9-30-2020 | Pass | PASS AC, 10-20-2020
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | PASS AC, 9-30-2020 | Pass | PASS AC, 10-20-2020
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | PASS AD, 9-30-2020 | Pass | PASS AD, 10-20-2020
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | PASS AD, 9-30-2020 | Pass | PASS AD, 10-20-2020
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | PASS AD, 9-30-2020 | Pass | PASS AD, 10-20-2020
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | PASS AD, 9-30-2020 | Pass | PASS AD, 10-20-2020
As a Player I want to sign-out so I can close my session when I am finished playing checkers. | Given PLAYER IS SIGNED IN AND ON PLAYER SELECTION PAGE when PLAYER CLICKS SIGN OUT BUTTON then PLAYER IS SIGNED OUT AND REDIRECTED HOME. |  |  | Pass | PASS AC, 10-20-2020
| Given PLAYER IS SIGNED IN AND IN GAME when PLAYER CLICKS SIGN OUT BUTTON then PLAYER IS SIGNED OUT AND REDIRECTED HOME. |  |  | Pass | PASS AC, 10-20-2020
| Given PLAYER IS SIGNED IN AND IN GAME when PLAYER CLICKS SIGN OUT BUTTON then PLAYER RESIGNS FROM GAME |  |  | Pass | PASS AC, 10-20-2020
| Given PLAYER IS SIGNED IN AND IN GAME when PLAYER CLICKS SIGN OUT BUTTON then OPPONENT PLAYER IS NOTIFIED OF RESIGNATION. |  |  | Pass | PASS AC, 10-20-2020
As a Player I want to be able to resign so that I can end an active game of checkers. | Given that I am in a game when I click the resign button then I am prompted for confirmation. |  |  | Pass | PASS JT, 10-20-2020
| Given that I click yes when I am prompted for confirmation then I am redirected to the home screen. |  |  | Pass | PASS JT, 10-20-2020
| Given that I resign when I am playing a game then I the game should end. |  |  | Pass | PASS JT, 10-20-2020
| Given my opponent resigns then I should see a notification telling me my opponent has resigned. |  |  | Pass | PASS JT, 10-20-2020
As a Player I want to select one of my pieces so that I can move it to an adjacent same-colored square. | Given I am in a game when I move my piece to an invalid square then the move will not be made and I can try again. |  |  | Pass | PASS AD, 10-8-2020
| Given I am in a game when I move my piece to a valid square then the move will be made. |  |  | Pass | PASS AD, 10-8-2020
| Given I made a valid move when I submit my move then the move will be finalized. |  |  | Pass | PASS AD, 10-8-2020
| Given I submitted my move when the screen refreshes then the move will be shown on screen. |  |  | Pass | PASS AD, 10-8-2020
| Given I submitted my move when it is finalized then it will no longer be my turn. |  |  | Pass | PASS AD, 10-8-2020
| Given I made a valid move when I click the "undo" button then my piece will be taken back to the starting place. |  |  | Pass | PASS AD, 10-8-2020
As a Player, I want to be able to jump my pieces over my opponent’s pieces to a vacant square to remove their pieces from play. | Given that an opponent piece is diagonal to one of my pieces, when I move my piece over that space then I should be able to take the opponent's piece. |  |  | Pass | PASS PO, 10-20-2020
| Given that I have taken an opponent piece, when I submit my turn, the opponent piece should disappear from the board. |  |  | Pass | PASS PO, 10-20-2020
| Given that I have taken an opponent piece and my piece has moved over the space, when I land across, the starting position of my piece should have no piece placed on it. |  |  | Pass | PASS PO, 10-20-2020
As a Player I want to select one of my pieces so that I can jump over several of the opponent player’s adjacent pieces if available. | Given that a MULTI move was made and there is enough space for one or more of such moves, when the first move had been made, I should be able to perform another such move. |  |  | Pass | PASS PO, 10-20-2020
| Given that I have made multiple moves in a row, when I submit my turn, all the opponent pieces I took must be removed from the board. |  |  | Pass | PASS PO, 10-20-2020
As a Player, I want to promote my pieces to King when they reach the king’s row to be able to move them backwards. | Given that a piece that joins the last row on their respective colour for the first time when I move a piece, then the piece changes itself to type KING. |  |  | Pass | PASS AD, 10-20-2020
| Given that the piece is King when it's my turn, I am able to move backwards 1 space. |  |  | Pass | PASS AD, 10-20-2020
| Given that the piece is King when it's my turn, it can operate backwards the same mechanics as any piece can forwards. |  |  | Pass | PASS AD, 10-20-2020
As a player I want to be able to see when I've won/lost the game so that I know when I can stop playing. | Given I make the winning move when I am playing a game then I expect the game to end.
Given I make the winning move when I am playing a game then I expect to receive a notification that I win.
Given my opponent makes the winning move when I am playing a game then I expect the game to end.
Given my opponent makes the winning move when I am playing a game then I expect to receive a notification that I lose.
Given I'm in a game when the game has ended then I expect to be taken back to the Home screen.
As a player, I want to be able to save a copy of the game I just played so I can watch it later. | Given I play a game of checkers then I expect each game movement to be recorded for replay later.
As a Player, I want to be able to choose a saved game to watch so I can review several games. | Given I've played at least one game of checkers in my session when I am on the homepage then I expect to see a list of my game recordings.
Given I click a recording link when I am on the homepage then I expect to see a replay of my game of checkers in a normal game view from my perspective.
Given I am watching a recording then I expect to see NEXT, PREVIOUS, and EXIT buttons that will allow me to progress to the next move, previous move, or exit the replay.
Given I am watching a recording when I press NEXT then I expect to see the next move in the game.
Given I am watching a recording when I press PREVIOUS then I expect to see the previous move in the game.
Given I am watching a recording when I press EXIT then I expect to be taken back to the home screen.
As a Player, I want to be able to choose to spectate an ongoing game after signing in so that I can watch a game without playing it. | Given I'm not logged in when I am at the home screen then I expect not to be able to spectate games.
Given I'm logged in when I'm on the Home screen then I should see a means to spectate current games.
Given I'm logged into the Home screen when I click a game to spectate then I expect to see that game.
As a Spectator, I want to be able to choose which ongoing game to watch, if there are multiple, so that I am not restricted to just watching the most recent game. | Given I'm spectating a game when I watch the screen then I expect it to update in real time.
Given I'm spectating a game when I interact with the board then I expect the board to not be influenced.
Given I'm spectating a game when I wish to exit then I should see a means to stop spectating.
Given I'm spectating a game when I exit spectator mode then I expect to be taken back to the Home screen.