## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
2201-swen-261-05-a | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | PASS JT, 9-29-2020
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. |  | PASS JT, 9-29-2020
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. |  | PASS JT, 9-29-2020
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. |  | PASS JT, 9-29-2020
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. |  | PASS PO, 9-29-2020
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | PASS PO, 9-29-2020
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | PASS PO, 9-29-2020
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | PASS AC, 9-30-2020
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | PASS AC, 9-30-2020
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | PASS AC, 9-30-2020
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | PASS AC, 9-30-2020
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | PASS AD, 9-30-2020
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | PASS AD, 9-30-2020
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | PASS AD, 9-30-2020
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | PASS AD, 9-30-2020
As a Player I want to sign-out so I can close my session when I am finished playing checkers.
As a Player I want to be able to resign so that I can end an active game of checkers.
As a Player I want to be able to resign so that I can end an active game of checkers.
As a Player I want to select one of my pieces so that I can move it to an adjacent same-colored square.
As a Player, I want to be able to jump my pieces over my opponent’s pieces to a vacant square to remove their pieces from play.
As a Player I want to select one of my pieces so that I can jump over several of the opponent player’s adjacent pieces if available.
As a Player, I want to promote my pieces to King when they reach the king’s row to be able to move them backwards.
As a player, I want to be able to save a copy of the game I just played so I can watch it later.
As a Player, I want to be able to choose a saved game to watch so I can review several games.
As a Player, I want to be able to choose to spectate an ongoing game after signing in so that I can watch a game without playing it.
As a Spectator, I want to be able to choose which ongoing game to watch, if there are multiple, so that I am not restricted to just watching the most recent game.